## Risk Register
Risk ID | Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score (L×I) | Treatment | Owner | Status
R001 | Email System | Phishing Attack | Employees unaware of phishing tactics, no email filtering | 4 | 4 | 16 | Mitigate | CISO | In Progress
R002 | Database | Unauthorized Access | No PAM system, shared admin passwords, no access logging | 4 | 4 | 16 | Mitigate | CTO | Not Started
R003 | Web Servers | Unpatched Vulnerability | No patch management process, servers updated manually | 4 | 3 | 12 | Mitigate | DevOps Lead | In Progress
R004 | Customer Data | Data Breach via Vendor | Third-party vendors have access, no agreements or monitoring | 3 | 5 | 15 | Mitigate | CISO | Not Started
R005 | All Systems | Insider Threat/Data Theft | Disgruntled employee with system access steals data | 2 | 5 | 10 | Accept | HR Manager | Monitored
R006 | Web Service | DDoS Attack | No DDoS protection, service goes down if attacked | 2 | 4 | 8 | Mitigate | Infrastructure | Not Started
R007 | Web Application | Missing Security Headers | XSS/Clickjacking vulnerabilities from missing headers | 3 | 3 | 9 | Mitigate | Dev Team | In Progress
R008 | User Accounts | Weak Password Policy | No password complexity requirements, easy to crack | 4 | 3 | 12 | Mitigate | CISO | Not Started
R009 | Critical Systems | No MFA on Login | Admin/critical accounts accessible with password only | 3 | 4 | 12 | Mitigate | CTO | Planned
R010 | Application | Outdated Dependencies | Old libraries with known vulnerabilities in codebase | 4 | 2 | 8 | Mitigate | Dev Team | In Progress

## Summary
Risk Register Summary
Company: | TechCo Pvt Ltd
Assessment Date: | 2026-06-03
Risk Metrics
Risk Level | Count | Percentage
Critical (21-25) | 0
High (13-20) | 3
Medium (6-12) | 7
Low (1-5) | 0
Total Risks | 10
Treatment Distribution
Treatment Type | Count
Mitigate | 9
Accept | 1
Transfer | 0
Avoid | 0
Status Distribution
Status | Count
Not Started | 4
In Progress | 4
Planned | 1
Monitored | 1